## How to use
Google Sheets version
Same checklist as module-checklist-by-role.docx. Status is as of 1 September 2026.
Open in Google Sheets
Option A | Upload this .xlsx to Google Drive → right-click → Open with → Google Sheets.
Option B | In Google Sheets: File → Import → Upload module-checklist-by-role.csv → Replace current sheet.
How to work the sheet
Filter | Open the All tasks tab, then Data → Create a filter. Filter Status or Role.
Status values | Completed · In progress · To do
Line format | Task title — Subtitle — Status (columns E, F, G on each tab)

## Summary
Roll-up
Role | Completed | In progress | To do | Total
Shared shell | 12 | 8 | 4 | 24
Admin module | 42 | 31 | 17 | 90
Sub-Franchisee module | 23 | 19 | 12 | 54
Franchisee module | 20 | 17 | 11 | 48
Retailer module | 17 | 12 | 7 | 36
All | 114 | 87 | 51 | 252
Suggested wiring order: Sub-Franchisee → Franchisee → Retailer → Admin. API-ready client and API wiring are in progress; QA / verification is to do.

## All tasks
Role | Module | Page | Path | Task title | Subtitle | Status
Shared shell | Authentication & chrome | Login | /login | Initial UI/UX | Email, password, demo account chips | Completed
Shared shell | Authentication & chrome | Login | /login | Frontend implementation | Session in localStorage; admin password restricted | Completed
Shared shell | Authentication & chrome | Login | /login | API-ready client | Need /api/v1 admin + finops resources | In progress
Shared shell | Authentication & chrome | Login | /login | API wiring | Still on localStorage | In progress
Shared shell | Authentication & chrome | Login | /login | QA / verification | Pending verification | To do
Shared shell | Authentication & chrome | Login | /login | Documentation | Documented in app-modules §3 | Completed
Shared shell | Authentication & chrome | Profile | /profile | Initial UI/UX | Read-only name, email, role, organization | Completed
Shared shell | Authentication & chrome | Profile | /profile | Frontend implementation | Reads AuthContext only; no edit | Completed
Shared shell | Authentication & chrome | Profile | /profile | API-ready client | Need /api/v1 admin + finops resources | In progress
Shared shell | Authentication & chrome | Profile | /profile | API wiring | Still on localStorage | In progress
Shared shell | Authentication & chrome | Profile | /profile | QA / verification | Pending verification | To do
Shared shell | Authentication & chrome | Profile | /profile | Documentation | Covered in app-modules / user guide | Completed
Shared shell | Authentication & chrome | Notifications | Header bell | Initial UI/UX | Pending credit requests + low/zero credits | Completed
Shared shell | Authentication & chrome | Notifications | Header bell | Frontend implementation | Per-org read state in localStorage | Completed
Shared shell | Authentication & chrome | Notifications | Header bell | API-ready client | Sub client has notifications.js; other roles do not | In progress
Shared shell | Authentication & chrome | Notifications | Header bell | API wiring | Bell still uses storage.js | In progress
Shared shell | Authentication & chrome | Notifications | Header bell | QA / verification | Pending verification | To do
Shared shell | Authentication & chrome | Notifications | Header bell | Documentation | Covered in app-modules / user guide | Completed
Shared shell | Authentication & chrome | Reset Demo Data | User menu | Initial UI/UX | Confirm in the user menu | Completed
Shared shell | Authentication & chrome | Reset Demo Data | User menu | Frontend implementation | Reseeds localStorage; keeps session if user still exists | Completed
Shared shell | Authentication & chrome | Reset Demo Data | User menu | API-ready client | Demo-only; not a production API | In progress
Shared shell | Authentication & chrome | Reset Demo Data | User menu | API wiring | Not applicable until a backend seed/reset exists | In progress
Shared shell | Authentication & chrome | Reset Demo Data | User menu | QA / verification | Pending verification | To do
Shared shell | Authentication & chrome | Reset Demo Data | User menu | Documentation | Called out in app-modules and user guides | Completed
Admin module | Financials Dashboard | Dashboard | /dashboard | Initial UI/UX | Upfront + billable monthly collections KPIs and tables | Completed
Admin module | Financials Dashboard | Dashboard | /dashboard | Frontend implementation | esarisari_franchise_collections ledger | Completed
Admin module | Financials Dashboard | Dashboard | /dashboard | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Financials Dashboard | Dashboard | /dashboard | API wiring | Still on localStorage | In progress
Admin module | Financials Dashboard | Dashboard | /dashboard | QA / verification | Pending verification | To do
Admin module | Financials Dashboard | Dashboard | /dashboard | Documentation | Covered in app-modules / user guide | Completed
Admin module | Clients & franchise setup | Clients list | /franchise-setup/clients | Initial UI/UX | Registered + seeded portfolio; Add New Client | Completed
Admin module | Clients & franchise setup | Clients list | /franchise-setup/clients | Frontend implementation | localStorage registered clients + demo portfolio | Completed
Admin module | Clients & franchise setup | Clients list | /franchise-setup/clients | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Clients & franchise setup | Clients list | /franchise-setup/clients | API wiring | Still on localStorage | In progress
Admin module | Clients & franchise setup | Clients list | /franchise-setup/clients | QA / verification | Pending verification | To do
Admin module | Clients & franchise setup | Clients list | /franchise-setup/clients | Documentation | Covered in app-modules / user guide | Completed
Admin module | Clients & franchise setup | Client details | /franchise-setup/clients/:clientId | Initial UI/UX | Activate, split, collections, territory | Completed
Admin module | Clients & franchise setup | Client details | /franchise-setup/clients/:clientId | Frontend implementation | Same collection ledger as Dashboard | Completed
Admin module | Clients & franchise setup | Client details | /franchise-setup/clients/:clientId | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Clients & franchise setup | Client details | /franchise-setup/clients/:clientId | API wiring | Still on localStorage | In progress
Admin module | Clients & franchise setup | Client details | /franchise-setup/clients/:clientId | QA / verification | Pending verification | To do
Admin module | Clients & franchise setup | Client details | /franchise-setup/clients/:clientId | Documentation | Covered in app-modules / user guide | Completed
Admin module | Clients & franchise setup | Onboarding step 1 — Client Info | /franchise-setup/onboarding/step-1 | Initial UI/UX | Admin credentials + company profile | Completed
Admin module | Clients & franchise setup | Onboarding step 1 — Client Info | /franchise-setup/onboarding/step-1 | Frontend implementation | Draft in esarisari_onboarding_client_info | Completed
Admin module | Clients & franchise setup | Onboarding step 1 — Client Info | /franchise-setup/onboarding/step-1 | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Clients & franchise setup | Onboarding step 1 — Client Info | /franchise-setup/onboarding/step-1 | API wiring | Still on localStorage | In progress
Admin module | Clients & franchise setup | Onboarding step 1 — Client Info | /franchise-setup/onboarding/step-1 | QA / verification | Pending verification | To do
Admin module | Clients & franchise setup | Onboarding step 1 — Client Info | /franchise-setup/onboarding/step-1 | Documentation | Covered in app-modules / user guide | Completed
Admin module | Clients & franchise setup | Onboarding step 2 — Franchise Setup | /franchise-setup/onboarding/step-2 | Initial UI/UX | Client type, packages, territory, fees | Completed
Admin module | Clients & franchise setup | Onboarding step 2 — Franchise Setup | /franchise-setup/onboarding/step-2 | Frontend implementation | Draft in esarisari_onboarding_franchise_setup | Completed
Admin module | Clients & franchise setup | Onboarding step 2 — Franchise Setup | /franchise-setup/onboarding/step-2 | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Clients & franchise setup | Onboarding step 2 — Franchise Setup | /franchise-setup/onboarding/step-2 | API wiring | Still on localStorage | In progress
Admin module | Clients & franchise setup | Onboarding step 2 — Franchise Setup | /franchise-setup/onboarding/step-2 | QA / verification | Pending verification | To do
Admin module | Clients & franchise setup | Onboarding step 2 — Franchise Setup | /franchise-setup/onboarding/step-2 | Documentation | Covered in app-modules / user guide | Completed
Admin module | Clients & franchise setup | Onboarding step 3 — Revenue Split | /franchise-setup/onboarding/step-3 | Initial UI/UX | Company vs this client only; downlines out of scope | Completed
Admin module | Clients & franchise setup | Onboarding step 3 — Revenue Split | /franchise-setup/onboarding/step-3 | Frontend implementation | esarisari_onboarding_revenue_split | Completed
Admin module | Clients & franchise setup | Onboarding step 3 — Revenue Split | /franchise-setup/onboarding/step-3 | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Clients & franchise setup | Onboarding step 3 — Revenue Split | /franchise-setup/onboarding/step-3 | API wiring | Still on localStorage | In progress
Admin module | Clients & franchise setup | Onboarding step 3 — Revenue Split | /franchise-setup/onboarding/step-3 | QA / verification | Pending verification | To do
Admin module | Clients & franchise setup | Onboarding step 3 — Revenue Split | /franchise-setup/onboarding/step-3 | Documentation | Covered in app-modules / user guide | Completed
Admin module | Clients & franchise setup | Onboarding step 4 — Review | /franchise-setup/onboarding/step-4 | Initial UI/UX | Confirm and Create Franchisee | Completed
Admin module | Clients & franchise setup | Onboarding step 4 — Review | /franchise-setup/onboarding/step-4 | Frontend implementation | Writes esarisari_registered_clients | Completed
Admin module | Clients & franchise setup | Onboarding step 4 — Review | /franchise-setup/onboarding/step-4 | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Clients & franchise setup | Onboarding step 4 — Review | /franchise-setup/onboarding/step-4 | API wiring | Still on localStorage | In progress
Admin module | Clients & franchise setup | Onboarding step 4 — Review | /franchise-setup/onboarding/step-4 | QA / verification | Pending verification | To do
Admin module | Clients & franchise setup | Onboarding step 4 — Review | /franchise-setup/onboarding/step-4 | Documentation | Covered in app-modules / user guide | Completed
Admin module | Wallets | Wallets directory | /wallets | Initial UI/UX | Network Available Credits directory | Completed
Admin module | Wallets | Wallets directory | /wallets | Frontend implementation | Operating wallets from localStorage | Completed
Admin module | Wallets | Wallets directory | /wallets | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Wallets | Wallets directory | /wallets | API wiring | Still on localStorage | In progress
Admin module | Wallets | Wallets directory | /wallets | QA / verification | Pending verification | To do
Admin module | Wallets | Wallets directory | /wallets | Documentation | Covered in app-modules / user guide | Completed
Admin module | Internet Credits | Internet Credits workspace | /funding | Initial UI/UX | Incoming, mine, direct release, approve/reject | Completed
Admin module | Internet Credits | Internet Credits workspace | /funding | Frontend implementation | fundingActions.js + localStorage ledgers | Completed
Admin module | Internet Credits | Internet Credits workspace | /funding | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Internet Credits | Internet Credits workspace | /funding | API wiring | Still on localStorage | In progress
Admin module | Internet Credits | Internet Credits workspace | /funding | QA / verification | Pending verification | To do
Admin module | Internet Credits | Internet Credits workspace | /funding | Documentation | Covered in app-modules / user guide | Completed
Admin module | Deposit Rates | Deposit Rates | /deposit-rates | Initial UI/UX | Admin → Sub hop overrides | Completed
Admin module | Deposit Rates | Deposit Rates | /deposit-rates | Frontend implementation | esarisari_deposit_rates | Completed
Admin module | Deposit Rates | Deposit Rates | /deposit-rates | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Deposit Rates | Deposit Rates | /deposit-rates | API wiring | Still on localStorage | In progress
Admin module | Deposit Rates | Deposit Rates | /deposit-rates | QA / verification | Pending verification | To do
Admin module | Deposit Rates | Deposit Rates | /deposit-rates | Documentation | Covered in app-modules / user guide | Completed
Admin module | Commission Settings | Commission Settings | /commission-settings | Initial UI/UX | Per-retailer split; Admin-editable platform fee | Completed
Admin module | Commission Settings | Commission Settings | /commission-settings | Frontend implementation | % of sales; Sub share is remainder for Admin | Completed
Admin module | Commission Settings | Commission Settings | /commission-settings | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Commission Settings | Commission Settings | /commission-settings | API wiring | Still on localStorage | In progress
Admin module | Commission Settings | Commission Settings | /commission-settings | QA / verification | Pending verification | To do
Admin module | Commission Settings | Commission Settings | /commission-settings | Documentation | Covered in app-modules / user guide | Completed
Admin module | Transactions | Transactions Ledger | /transactions | Initial UI/UX | Sales table + franchise setup collections panel | Completed
Admin module | Transactions | Transactions Ledger | /transactions | Frontend implementation | Empty sales seed; collections share Dashboard ledger | Completed
Admin module | Transactions | Transactions Ledger | /transactions | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Transactions | Transactions Ledger | /transactions | API wiring | Still on localStorage | In progress
Admin module | Transactions | Transactions Ledger | /transactions | QA / verification | Pending verification | To do
Admin module | Transactions | Transactions Ledger | /transactions | Documentation | Covered in app-modules / user guide | Completed
Admin module | Revenue | Revenue | /revenue | Initial UI/UX | IC earnings + sales commission + collections | Completed
Admin module | Revenue | Revenue | /revenue | Frontend implementation | Two money streams stay separate from collections cash | Completed
Admin module | Revenue | Revenue | /revenue | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Revenue | Revenue | /revenue | API wiring | Still on localStorage | In progress
Admin module | Revenue | Revenue | /revenue | QA / verification | Pending verification | To do
Admin module | Revenue | Revenue | /revenue | Documentation | Covered in app-modules / user guide | Completed
Admin module | Reports | Reports | /reports | Initial UI/UX | Network tables, Sub revenue-sharing sheet, CSV, collections | Completed
Admin module | Reports | Reports | /reports | Frontend implementation | Client-sheet Sub report included for Admin too | Completed
Admin module | Reports | Reports | /reports | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Reports | Reports | /reports | API wiring | Still on localStorage | In progress
Admin module | Reports | Reports | /reports | QA / verification | Pending verification | To do
Admin module | Reports | Reports | /reports | Documentation | Covered in app-modules / user guide | Completed
Admin module | Leftovers (not in sidebar) | Organizations | /organizations | Initial UI/UX | Placeholder copy; removed from nav | To do
Admin module | Leftovers (not in sidebar) | Organizations | /organizations | Frontend implementation | Route exists; not a product surface | To do
Admin module | Leftovers (not in sidebar) | Organizations | /organizations | API-ready client | No contract yet | In progress
Admin module | Leftovers (not in sidebar) | Organizations | /organizations | API wiring | Blocked on frontend + API | In progress
Admin module | Leftovers (not in sidebar) | Organizations | /organizations | QA / verification | Page is not live | To do
Admin module | Leftovers (not in sidebar) | Organizations | /organizations | Documentation | Placeholder only in app-modules | In progress
Sub-Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | Initial UI/UX | Greyed nav item only; Admin Financials is not this role | Completed
Sub-Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | Frontend implementation | Role-specific Sub dashboard | To do
Sub-Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | API-ready client | Not in the current Sub API contract | In progress
Sub-Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | API wiring | Blocked on product decision | In progress
Sub-Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | QA / verification | Route is blocked for this role | To do
Sub-Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | Documentation | Noted as greyed in app-modules | Completed
Sub-Franchisee module | Franchisees (greyed) | Franchisees | /franchisees | Initial UI/UX | Greyed nav; no AppRoutes entry | To do
Sub-Franchisee module | Franchisees (greyed) | Franchisees | /franchisees | Frontend implementation | Placeholder page file only | To do
Sub-Franchisee module | Franchisees (greyed) | Franchisees | /franchisees | API-ready client | No contract yet | In progress
Sub-Franchisee module | Franchisees (greyed) | Franchisees | /franchisees | API wiring | Blocked on frontend + API | In progress
Sub-Franchisee module | Franchisees (greyed) | Franchisees | /franchisees | QA / verification | Page is not live | To do
Sub-Franchisee module | Franchisees (greyed) | Franchisees | /franchisees | Documentation | Placeholder only in app-modules | In progress
Sub-Franchisee module | Wallets | Wallet Management | /wallet-management | Initial UI/UX | Own org + franchisee + retailer credits directory | Completed
Sub-Franchisee module | Wallets | Wallet Management | /wallet-management | Frontend implementation | Read-only; activity sheet from transfers | Completed
Sub-Franchisee module | Wallets | Wallet Management | /wallet-management | API-ready client | Unwired client in src/services/api/subfranchisor | In progress
Sub-Franchisee module | Wallets | Wallet Management | /wallet-management | API wiring | Do not swap loaders until VITE_API_BASE_URL is set | In progress
Sub-Franchisee module | Wallets | Wallet Management | /wallet-management | QA / verification | Pending verification | To do
Sub-Franchisee module | Wallets | Wallet Management | /wallet-management | Documentation | Covered in app-modules / user guide | Completed
Sub-Franchisee module | Internet Credits | Internet Credits workspace | /funding | Initial UI/UX | Request from Admin; release/reject franchisee requests; direct release | Completed
Sub-Franchisee module | Internet Credits | Internet Credits workspace | /funding | Frontend implementation | releaseSource=balance; hop admin_to_sub / sub_to_franchisee | Completed
Sub-Franchisee module | Internet Credits | Internet Credits workspace | /funding | API-ready client | Unwired client in src/services/api/subfranchisor | In progress
Sub-Franchisee module | Internet Credits | Internet Credits workspace | /funding | API wiring | Do not swap loaders until VITE_API_BASE_URL is set | In progress
Sub-Franchisee module | Internet Credits | Internet Credits workspace | /funding | QA / verification | Pending verification | To do
Sub-Franchisee module | Internet Credits | Internet Credits workspace | /funding | Documentation | Covered in app-modules / user guide | Completed
Sub-Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | Initial UI/UX | Sub → Franchisee hop (default 70%) | Completed
Sub-Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | Frontend implementation | Overrides in esarisari_deposit_rates | Completed
Sub-Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | API-ready client | Unwired client in src/services/api/subfranchisor | In progress
Sub-Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | API wiring | Do not swap loaders until VITE_API_BASE_URL is set | In progress
Sub-Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | QA / verification | Pending verification | To do
Sub-Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | Documentation | Covered in app-modules / user guide | Completed
Sub-Franchisee module | Commission Settings | Commission Settings | /commission-settings | Initial UI/UX | Retailer, franchisee, Your Share editable; platform fee read-only | Completed
Sub-Franchisee module | Commission Settings | Commission Settings | /commission-settings | Frontend implementation | Split is % of sales; total must equal 100% | Completed
Sub-Franchisee module | Commission Settings | Commission Settings | /commission-settings | API-ready client | Unwired client in src/services/api/subfranchisor | In progress
Sub-Franchisee module | Commission Settings | Commission Settings | /commission-settings | API wiring | Do not swap loaders until VITE_API_BASE_URL is set | In progress
Sub-Franchisee module | Commission Settings | Commission Settings | /commission-settings | QA / verification | Pending verification | To do
Sub-Franchisee module | Commission Settings | Commission Settings | /commission-settings | Documentation | Covered in app-modules / user guide | Completed
Sub-Franchisee module | Transactions | Transactions Ledger | /transactions | Initial UI/UX | Network sales; Your Share column; no Record sale | Completed
Sub-Franchisee module | Transactions | Transactions Ledger | /transactions | Frontend implementation | Scoped by subfranchiseeOrganizationId | Completed
Sub-Franchisee module | Transactions | Transactions Ledger | /transactions | API-ready client | Unwired client in src/services/api/subfranchisor | In progress
Sub-Franchisee module | Transactions | Transactions Ledger | /transactions | API wiring | Do not swap loaders until VITE_API_BASE_URL is set | In progress
Sub-Franchisee module | Transactions | Transactions Ledger | /transactions | QA / verification | Pending verification | To do
Sub-Franchisee module | Transactions | Transactions Ledger | /transactions | Documentation | Covered in app-modules / user guide | Completed
Sub-Franchisee module | Revenue | Revenue | /revenue | Initial UI/UX | IC spread earnings + sales commission | Completed
Sub-Franchisee module | Revenue | Revenue | /revenue | Frontend implementation | credit_spread mode; no franchise collections | Completed
Sub-Franchisee module | Revenue | Revenue | /revenue | API-ready client | Unwired client in src/services/api/subfranchisor | In progress
Sub-Franchisee module | Revenue | Revenue | /revenue | API wiring | Do not swap loaders until VITE_API_BASE_URL is set | In progress
Sub-Franchisee module | Revenue | Revenue | /revenue | QA / verification | Pending verification | To do
Sub-Franchisee module | Revenue | Revenue | /revenue | Documentation | Covered in app-modules / user guide | Completed
Sub-Franchisee module | Reports | Reports | /reports | Initial UI/UX | Revenue Sharing Sub-Franchisee table + CSV + network commissions | Completed
Sub-Franchisee module | Reports | Reports | /reports | Frontend implementation | Client-sheet layout; platform fee excluded from Total Revenue | Completed
Sub-Franchisee module | Reports | Reports | /reports | API-ready client | Unwired client in src/services/api/subfranchisor | In progress
Sub-Franchisee module | Reports | Reports | /reports | API wiring | Do not swap loaders until VITE_API_BASE_URL is set | In progress
Sub-Franchisee module | Reports | Reports | /reports | QA / verification | Pending verification | To do
Sub-Franchisee module | Reports | Reports | /reports | Documentation | Covered in app-modules / user guide | Completed
Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | Initial UI/UX | Greyed nav item only | Completed
Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | Frontend implementation | Role-specific franchisee dashboard | To do
Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | API-ready client | Not started | In progress
Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | API wiring | Blocked on product + API | In progress
Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | QA / verification | Route is blocked | To do
Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | Documentation | Noted as greyed in app-modules | Completed
Franchisee module | Retailers (greyed) | Retailers | /retailers | Initial UI/UX | Greyed nav; placeholder page; route blocked | To do
Franchisee module | Retailers (greyed) | Retailers | /retailers | Frontend implementation | No retailer directory product yet | To do
Franchisee module | Retailers (greyed) | Retailers | /retailers | API-ready client | No contract yet | In progress
Franchisee module | Retailers (greyed) | Retailers | /retailers | API wiring | Blocked on frontend + API | In progress
Franchisee module | Retailers (greyed) | Retailers | /retailers | QA / verification | Page is not live | To do
Franchisee module | Retailers (greyed) | Retailers | /retailers | Documentation | Placeholder only in app-modules | In progress
Franchisee module | Wallets | Wallet Management | /wallet-management | Initial UI/UX | Own + retailer credits directory | Completed
Franchisee module | Wallets | Wallet Management | /wallet-management | Frontend implementation | Read-only localStorage wallets | Completed
Franchisee module | Wallets | Wallet Management | /wallet-management | API-ready client | Need franchisee API module (same pattern as Sub) | In progress
Franchisee module | Wallets | Wallet Management | /wallet-management | API wiring | Still on localStorage | In progress
Franchisee module | Wallets | Wallet Management | /wallet-management | QA / verification | Pending verification | To do
Franchisee module | Wallets | Wallet Management | /wallet-management | Documentation | Covered in app-modules / user guide | Completed
Franchisee module | Internet Credits | Internet Credits workspace | /funding | Initial UI/UX | Request from Sub; release/reject retailer requests; direct release | Completed
Franchisee module | Internet Credits | Internet Credits workspace | /funding | Frontend implementation | Hop sub_to_franchisee / franchisee_to_retailer | Completed
Franchisee module | Internet Credits | Internet Credits workspace | /funding | API-ready client | Need franchisee API module (same pattern as Sub) | In progress
Franchisee module | Internet Credits | Internet Credits workspace | /funding | API wiring | Still on localStorage | In progress
Franchisee module | Internet Credits | Internet Credits workspace | /funding | QA / verification | Pending verification | To do
Franchisee module | Internet Credits | Internet Credits workspace | /funding | Documentation | Covered in app-modules / user guide | Completed
Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | Initial UI/UX | Franchisee → Retailer hop (default 80%) | Completed
Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | Frontend implementation | Downline overrides only | Completed
Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | API-ready client | Need franchisee API module (same pattern as Sub) | In progress
Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | API wiring | Still on localStorage | In progress
Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | QA / verification | Pending verification | To do
Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | Documentation | Covered in app-modules / user guide | Completed
Franchisee module | Transactions | Transactions Ledger | /transactions | Initial UI/UX | Retailer sales under this franchisee | Completed
Franchisee module | Transactions | Transactions Ledger | /transactions | Frontend implementation | Scoped by franchiseeOrganizationId | Completed
Franchisee module | Transactions | Transactions Ledger | /transactions | API-ready client | Need franchisee API module (same pattern as Sub) | In progress
Franchisee module | Transactions | Transactions Ledger | /transactions | API wiring | Still on localStorage | In progress
Franchisee module | Transactions | Transactions Ledger | /transactions | QA / verification | Pending verification | To do
Franchisee module | Transactions | Transactions Ledger | /transactions | Documentation | Covered in app-modules / user guide | Completed
Franchisee module | Revenue | Revenue | /revenue | Initial UI/UX | IC spread + sales commission | Completed
Franchisee module | Revenue | Revenue | /revenue | Frontend implementation | credit_spread mode | Completed
Franchisee module | Revenue | Revenue | /revenue | API-ready client | Need franchisee API module (same pattern as Sub) | In progress
Franchisee module | Revenue | Revenue | /revenue | API wiring | Still on localStorage | In progress
Franchisee module | Revenue | Revenue | /revenue | QA / verification | Pending verification | To do
Franchisee module | Revenue | Revenue | /revenue | Documentation | Covered in app-modules / user guide | Completed
Franchisee module | Reports | Reports | /reports | Initial UI/UX | Retailer commissions + IC earnings; no Sub sheet table | Completed
Franchisee module | Reports | Reports | /reports | Frontend implementation | Role config hides Sub revenue-sharing export | Completed
Franchisee module | Reports | Reports | /reports | API-ready client | Need franchisee API module (same pattern as Sub) | In progress
Franchisee module | Reports | Reports | /reports | API wiring | Still on localStorage | In progress
Franchisee module | Reports | Reports | /reports | QA / verification | Pending verification | To do
Franchisee module | Reports | Reports | /reports | Documentation | Covered in app-modules / user guide | Completed
Retailer module | Dashboard (greyed) | Dashboard | /dashboard | Initial UI/UX | Greyed nav item only | Completed
Retailer module | Dashboard (greyed) | Dashboard | /dashboard | Frontend implementation | Role-specific retailer dashboard | To do
Retailer module | Dashboard (greyed) | Dashboard | /dashboard | API-ready client | Not started | In progress
Retailer module | Dashboard (greyed) | Dashboard | /dashboard | API wiring | Blocked on product + API | In progress
Retailer module | Dashboard (greyed) | Dashboard | /dashboard | QA / verification | Route is blocked | To do
Retailer module | Dashboard (greyed) | Dashboard | /dashboard | Documentation | Noted as greyed in app-modules | Completed
Retailer module | Wallet | Wallet | /wallet | Initial UI/UX | Available Credits, sale margin, request CTA | Completed
Retailer module | Wallet | Wallet | /wallet | Frontend implementation | Retailer operating wallet; cannot record sales here | Completed
Retailer module | Wallet | Wallet | /wallet | API-ready client | Need retailer API module | In progress
Retailer module | Wallet | Wallet | /wallet | API wiring | Still on localStorage | In progress
Retailer module | Wallet | Wallet | /wallet | QA / verification | Pending verification | To do
Retailer module | Wallet | Wallet | /wallet | Documentation | Covered in app-modules / user guide | Completed
Retailer module | Internet Credits | Request Funding | /request-funding | Initial UI/UX | Request-only workspace to Franchisee | Completed
Retailer module | Internet Credits | Request Funding | /request-funding | Frontend implementation | Same FundingWorkspacePage; no incoming / direct release | Completed
Retailer module | Internet Credits | Request Funding | /request-funding | API-ready client | Need retailer API module | In progress
Retailer module | Internet Credits | Request Funding | /request-funding | API wiring | Still on localStorage | In progress
Retailer module | Internet Credits | Request Funding | /request-funding | QA / verification | Pending verification | To do
Retailer module | Internet Credits | Request Funding | /request-funding | Documentation | Covered in app-modules / user guide | Completed
Retailer module | Transactions | Transactions Ledger | /transactions | Initial UI/UX | Own sales + Record demo sale | Completed
Retailer module | Transactions | Transactions Ledger | /transactions | Frontend implementation | Burns ~97% credits; stamps commission % of sales | Completed
Retailer module | Transactions | Transactions Ledger | /transactions | API-ready client | Need retailer API module | In progress
Retailer module | Transactions | Transactions Ledger | /transactions | API wiring | Still on localStorage | In progress
Retailer module | Transactions | Transactions Ledger | /transactions | QA / verification | Pending verification | To do
Retailer module | Transactions | Transactions Ledger | /transactions | Documentation | Covered in app-modules / user guide | Completed
Retailer module | Revenue | Revenue | /revenue | Initial UI/UX | Your commission, sales volume, credits consumed | Completed
Retailer module | Revenue | Revenue | /revenue | Frontend implementation | No IC earnings / Total earnings cards | Completed
Retailer module | Revenue | Revenue | /revenue | API-ready client | Need retailer API module | In progress
Retailer module | Revenue | Revenue | /revenue | API wiring | Still on localStorage | In progress
Retailer module | Revenue | Revenue | /revenue | QA / verification | Pending verification | To do
Retailer module | Revenue | Revenue | /revenue | Documentation | Covered in app-modules / user guide | Completed
Retailer module | Reports | Reports | /reports | Initial UI/UX | Own sales commission + volume; limited CSV | Completed
Retailer module | Reports | Reports | /reports | Frontend implementation | No network tables or Sub sheet | Completed
Retailer module | Reports | Reports | /reports | API-ready client | Need retailer API module | In progress
Retailer module | Reports | Reports | /reports | API wiring | Still on localStorage | In progress
Retailer module | Reports | Reports | /reports | QA / verification | Pending verification | To do
Retailer module | Reports | Reports | /reports | Documentation | Covered in app-modules / user guide | Completed

## Shared shell
Role | Module | Page | Path | Task title | Subtitle | Status
Shared shell | Authentication & chrome | Login | /login | Initial UI/UX | Email, password, demo account chips | Completed
Shared shell | Authentication & chrome | Login | /login | Frontend implementation | Session in localStorage; admin password restricted | Completed
Shared shell | Authentication & chrome | Login | /login | API-ready client | Need /api/v1 admin + finops resources | In progress
Shared shell | Authentication & chrome | Login | /login | API wiring | Still on localStorage | In progress
Shared shell | Authentication & chrome | Login | /login | QA / verification | Pending verification | To do
Shared shell | Authentication & chrome | Login | /login | Documentation | Documented in app-modules §3 | Completed
Shared shell | Authentication & chrome | Profile | /profile | Initial UI/UX | Read-only name, email, role, organization | Completed
Shared shell | Authentication & chrome | Profile | /profile | Frontend implementation | Reads AuthContext only; no edit | Completed
Shared shell | Authentication & chrome | Profile | /profile | API-ready client | Need /api/v1 admin + finops resources | In progress
Shared shell | Authentication & chrome | Profile | /profile | API wiring | Still on localStorage | In progress
Shared shell | Authentication & chrome | Profile | /profile | QA / verification | Pending verification | To do
Shared shell | Authentication & chrome | Profile | /profile | Documentation | Covered in app-modules / user guide | Completed
Shared shell | Authentication & chrome | Notifications | Header bell | Initial UI/UX | Pending credit requests + low/zero credits | Completed
Shared shell | Authentication & chrome | Notifications | Header bell | Frontend implementation | Per-org read state in localStorage | Completed
Shared shell | Authentication & chrome | Notifications | Header bell | API-ready client | Sub client has notifications.js; other roles do not | In progress
Shared shell | Authentication & chrome | Notifications | Header bell | API wiring | Bell still uses storage.js | In progress
Shared shell | Authentication & chrome | Notifications | Header bell | QA / verification | Pending verification | To do
Shared shell | Authentication & chrome | Notifications | Header bell | Documentation | Covered in app-modules / user guide | Completed
Shared shell | Authentication & chrome | Reset Demo Data | User menu | Initial UI/UX | Confirm in the user menu | Completed
Shared shell | Authentication & chrome | Reset Demo Data | User menu | Frontend implementation | Reseeds localStorage; keeps session if user still exists | Completed
Shared shell | Authentication & chrome | Reset Demo Data | User menu | API-ready client | Demo-only; not a production API | In progress
Shared shell | Authentication & chrome | Reset Demo Data | User menu | API wiring | Not applicable until a backend seed/reset exists | In progress
Shared shell | Authentication & chrome | Reset Demo Data | User menu | QA / verification | Pending verification | To do
Shared shell | Authentication & chrome | Reset Demo Data | User menu | Documentation | Called out in app-modules and user guides | Completed

## Admin
Role | Module | Page | Path | Task title | Subtitle | Status
Admin module | Financials Dashboard | Dashboard | /dashboard | Initial UI/UX | Upfront + billable monthly collections KPIs and tables | Completed
Admin module | Financials Dashboard | Dashboard | /dashboard | Frontend implementation | esarisari_franchise_collections ledger | Completed
Admin module | Financials Dashboard | Dashboard | /dashboard | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Financials Dashboard | Dashboard | /dashboard | API wiring | Still on localStorage | In progress
Admin module | Financials Dashboard | Dashboard | /dashboard | QA / verification | Pending verification | To do
Admin module | Financials Dashboard | Dashboard | /dashboard | Documentation | Covered in app-modules / user guide | Completed
Admin module | Clients & franchise setup | Clients list | /franchise-setup/clients | Initial UI/UX | Registered + seeded portfolio; Add New Client | Completed
Admin module | Clients & franchise setup | Clients list | /franchise-setup/clients | Frontend implementation | localStorage registered clients + demo portfolio | Completed
Admin module | Clients & franchise setup | Clients list | /franchise-setup/clients | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Clients & franchise setup | Clients list | /franchise-setup/clients | API wiring | Still on localStorage | In progress
Admin module | Clients & franchise setup | Clients list | /franchise-setup/clients | QA / verification | Pending verification | To do
Admin module | Clients & franchise setup | Clients list | /franchise-setup/clients | Documentation | Covered in app-modules / user guide | Completed
Admin module | Clients & franchise setup | Client details | /franchise-setup/clients/:clientId | Initial UI/UX | Activate, split, collections, territory | Completed
Admin module | Clients & franchise setup | Client details | /franchise-setup/clients/:clientId | Frontend implementation | Same collection ledger as Dashboard | Completed
Admin module | Clients & franchise setup | Client details | /franchise-setup/clients/:clientId | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Clients & franchise setup | Client details | /franchise-setup/clients/:clientId | API wiring | Still on localStorage | In progress
Admin module | Clients & franchise setup | Client details | /franchise-setup/clients/:clientId | QA / verification | Pending verification | To do
Admin module | Clients & franchise setup | Client details | /franchise-setup/clients/:clientId | Documentation | Covered in app-modules / user guide | Completed
Admin module | Clients & franchise setup | Onboarding step 1 — Client Info | /franchise-setup/onboarding/step-1 | Initial UI/UX | Admin credentials + company profile | Completed
Admin module | Clients & franchise setup | Onboarding step 1 — Client Info | /franchise-setup/onboarding/step-1 | Frontend implementation | Draft in esarisari_onboarding_client_info | Completed
Admin module | Clients & franchise setup | Onboarding step 1 — Client Info | /franchise-setup/onboarding/step-1 | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Clients & franchise setup | Onboarding step 1 — Client Info | /franchise-setup/onboarding/step-1 | API wiring | Still on localStorage | In progress
Admin module | Clients & franchise setup | Onboarding step 1 — Client Info | /franchise-setup/onboarding/step-1 | QA / verification | Pending verification | To do
Admin module | Clients & franchise setup | Onboarding step 1 — Client Info | /franchise-setup/onboarding/step-1 | Documentation | Covered in app-modules / user guide | Completed
Admin module | Clients & franchise setup | Onboarding step 2 — Franchise Setup | /franchise-setup/onboarding/step-2 | Initial UI/UX | Client type, packages, territory, fees | Completed
Admin module | Clients & franchise setup | Onboarding step 2 — Franchise Setup | /franchise-setup/onboarding/step-2 | Frontend implementation | Draft in esarisari_onboarding_franchise_setup | Completed
Admin module | Clients & franchise setup | Onboarding step 2 — Franchise Setup | /franchise-setup/onboarding/step-2 | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Clients & franchise setup | Onboarding step 2 — Franchise Setup | /franchise-setup/onboarding/step-2 | API wiring | Still on localStorage | In progress
Admin module | Clients & franchise setup | Onboarding step 2 — Franchise Setup | /franchise-setup/onboarding/step-2 | QA / verification | Pending verification | To do
Admin module | Clients & franchise setup | Onboarding step 2 — Franchise Setup | /franchise-setup/onboarding/step-2 | Documentation | Covered in app-modules / user guide | Completed
Admin module | Clients & franchise setup | Onboarding step 3 — Revenue Split | /franchise-setup/onboarding/step-3 | Initial UI/UX | Company vs this client only; downlines out of scope | Completed
Admin module | Clients & franchise setup | Onboarding step 3 — Revenue Split | /franchise-setup/onboarding/step-3 | Frontend implementation | esarisari_onboarding_revenue_split | Completed
Admin module | Clients & franchise setup | Onboarding step 3 — Revenue Split | /franchise-setup/onboarding/step-3 | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Clients & franchise setup | Onboarding step 3 — Revenue Split | /franchise-setup/onboarding/step-3 | API wiring | Still on localStorage | In progress
Admin module | Clients & franchise setup | Onboarding step 3 — Revenue Split | /franchise-setup/onboarding/step-3 | QA / verification | Pending verification | To do
Admin module | Clients & franchise setup | Onboarding step 3 — Revenue Split | /franchise-setup/onboarding/step-3 | Documentation | Covered in app-modules / user guide | Completed
Admin module | Clients & franchise setup | Onboarding step 4 — Review | /franchise-setup/onboarding/step-4 | Initial UI/UX | Confirm and Create Franchisee | Completed
Admin module | Clients & franchise setup | Onboarding step 4 — Review | /franchise-setup/onboarding/step-4 | Frontend implementation | Writes esarisari_registered_clients | Completed
Admin module | Clients & franchise setup | Onboarding step 4 — Review | /franchise-setup/onboarding/step-4 | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Clients & franchise setup | Onboarding step 4 — Review | /franchise-setup/onboarding/step-4 | API wiring | Still on localStorage | In progress
Admin module | Clients & franchise setup | Onboarding step 4 — Review | /franchise-setup/onboarding/step-4 | QA / verification | Pending verification | To do
Admin module | Clients & franchise setup | Onboarding step 4 — Review | /franchise-setup/onboarding/step-4 | Documentation | Covered in app-modules / user guide | Completed
Admin module | Wallets | Wallets directory | /wallets | Initial UI/UX | Network Available Credits directory | Completed
Admin module | Wallets | Wallets directory | /wallets | Frontend implementation | Operating wallets from localStorage | Completed
Admin module | Wallets | Wallets directory | /wallets | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Wallets | Wallets directory | /wallets | API wiring | Still on localStorage | In progress
Admin module | Wallets | Wallets directory | /wallets | QA / verification | Pending verification | To do
Admin module | Wallets | Wallets directory | /wallets | Documentation | Covered in app-modules / user guide | Completed
Admin module | Internet Credits | Internet Credits workspace | /funding | Initial UI/UX | Incoming, mine, direct release, approve/reject | Completed
Admin module | Internet Credits | Internet Credits workspace | /funding | Frontend implementation | fundingActions.js + localStorage ledgers | Completed
Admin module | Internet Credits | Internet Credits workspace | /funding | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Internet Credits | Internet Credits workspace | /funding | API wiring | Still on localStorage | In progress
Admin module | Internet Credits | Internet Credits workspace | /funding | QA / verification | Pending verification | To do
Admin module | Internet Credits | Internet Credits workspace | /funding | Documentation | Covered in app-modules / user guide | Completed
Admin module | Deposit Rates | Deposit Rates | /deposit-rates | Initial UI/UX | Admin → Sub hop overrides | Completed
Admin module | Deposit Rates | Deposit Rates | /deposit-rates | Frontend implementation | esarisari_deposit_rates | Completed
Admin module | Deposit Rates | Deposit Rates | /deposit-rates | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Deposit Rates | Deposit Rates | /deposit-rates | API wiring | Still on localStorage | In progress
Admin module | Deposit Rates | Deposit Rates | /deposit-rates | QA / verification | Pending verification | To do
Admin module | Deposit Rates | Deposit Rates | /deposit-rates | Documentation | Covered in app-modules / user guide | Completed
Admin module | Commission Settings | Commission Settings | /commission-settings | Initial UI/UX | Per-retailer split; Admin-editable platform fee | Completed
Admin module | Commission Settings | Commission Settings | /commission-settings | Frontend implementation | % of sales; Sub share is remainder for Admin | Completed
Admin module | Commission Settings | Commission Settings | /commission-settings | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Commission Settings | Commission Settings | /commission-settings | API wiring | Still on localStorage | In progress
Admin module | Commission Settings | Commission Settings | /commission-settings | QA / verification | Pending verification | To do
Admin module | Commission Settings | Commission Settings | /commission-settings | Documentation | Covered in app-modules / user guide | Completed
Admin module | Transactions | Transactions Ledger | /transactions | Initial UI/UX | Sales table + franchise setup collections panel | Completed
Admin module | Transactions | Transactions Ledger | /transactions | Frontend implementation | Empty sales seed; collections share Dashboard ledger | Completed
Admin module | Transactions | Transactions Ledger | /transactions | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Transactions | Transactions Ledger | /transactions | API wiring | Still on localStorage | In progress
Admin module | Transactions | Transactions Ledger | /transactions | QA / verification | Pending verification | To do
Admin module | Transactions | Transactions Ledger | /transactions | Documentation | Covered in app-modules / user guide | Completed
Admin module | Revenue | Revenue | /revenue | Initial UI/UX | IC earnings + sales commission + collections | Completed
Admin module | Revenue | Revenue | /revenue | Frontend implementation | Two money streams stay separate from collections cash | Completed
Admin module | Revenue | Revenue | /revenue | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Revenue | Revenue | /revenue | API wiring | Still on localStorage | In progress
Admin module | Revenue | Revenue | /revenue | QA / verification | Pending verification | To do
Admin module | Revenue | Revenue | /revenue | Documentation | Covered in app-modules / user guide | Completed
Admin module | Reports | Reports | /reports | Initial UI/UX | Network tables, Sub revenue-sharing sheet, CSV, collections | Completed
Admin module | Reports | Reports | /reports | Frontend implementation | Client-sheet Sub report included for Admin too | Completed
Admin module | Reports | Reports | /reports | API-ready client | Need /api/v1 admin + finops resources | In progress
Admin module | Reports | Reports | /reports | API wiring | Still on localStorage | In progress
Admin module | Reports | Reports | /reports | QA / verification | Pending verification | To do
Admin module | Reports | Reports | /reports | Documentation | Covered in app-modules / user guide | Completed
Admin module | Leftovers (not in sidebar) | Organizations | /organizations | Initial UI/UX | Placeholder copy; removed from nav | To do
Admin module | Leftovers (not in sidebar) | Organizations | /organizations | Frontend implementation | Route exists; not a product surface | To do
Admin module | Leftovers (not in sidebar) | Organizations | /organizations | API-ready client | No contract yet | In progress
Admin module | Leftovers (not in sidebar) | Organizations | /organizations | API wiring | Blocked on frontend + API | In progress
Admin module | Leftovers (not in sidebar) | Organizations | /organizations | QA / verification | Page is not live | To do
Admin module | Leftovers (not in sidebar) | Organizations | /organizations | Documentation | Placeholder only in app-modules | In progress

## Sub-Franchisee
Role | Module | Page | Path | Task title | Subtitle | Status
Sub-Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | Initial UI/UX | Greyed nav item only; Admin Financials is not this role | Completed
Sub-Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | Frontend implementation | Role-specific Sub dashboard | To do
Sub-Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | API-ready client | Not in the current Sub API contract | In progress
Sub-Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | API wiring | Blocked on product decision | In progress
Sub-Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | QA / verification | Route is blocked for this role | To do
Sub-Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | Documentation | Noted as greyed in app-modules | Completed
Sub-Franchisee module | Franchisees (greyed) | Franchisees | /franchisees | Initial UI/UX | Greyed nav; no AppRoutes entry | To do
Sub-Franchisee module | Franchisees (greyed) | Franchisees | /franchisees | Frontend implementation | Placeholder page file only | To do
Sub-Franchisee module | Franchisees (greyed) | Franchisees | /franchisees | API-ready client | No contract yet | In progress
Sub-Franchisee module | Franchisees (greyed) | Franchisees | /franchisees | API wiring | Blocked on frontend + API | In progress
Sub-Franchisee module | Franchisees (greyed) | Franchisees | /franchisees | QA / verification | Page is not live | To do
Sub-Franchisee module | Franchisees (greyed) | Franchisees | /franchisees | Documentation | Placeholder only in app-modules | In progress
Sub-Franchisee module | Wallets | Wallet Management | /wallet-management | Initial UI/UX | Own org + franchisee + retailer credits directory | Completed
Sub-Franchisee module | Wallets | Wallet Management | /wallet-management | Frontend implementation | Read-only; activity sheet from transfers | Completed
Sub-Franchisee module | Wallets | Wallet Management | /wallet-management | API-ready client | Unwired client in src/services/api/subfranchisor | In progress
Sub-Franchisee module | Wallets | Wallet Management | /wallet-management | API wiring | Do not swap loaders until VITE_API_BASE_URL is set | In progress
Sub-Franchisee module | Wallets | Wallet Management | /wallet-management | QA / verification | Pending verification | To do
Sub-Franchisee module | Wallets | Wallet Management | /wallet-management | Documentation | Covered in app-modules / user guide | Completed
Sub-Franchisee module | Internet Credits | Internet Credits workspace | /funding | Initial UI/UX | Request from Admin; release/reject franchisee requests; direct release | Completed
Sub-Franchisee module | Internet Credits | Internet Credits workspace | /funding | Frontend implementation | releaseSource=balance; hop admin_to_sub / sub_to_franchisee | Completed
Sub-Franchisee module | Internet Credits | Internet Credits workspace | /funding | API-ready client | Unwired client in src/services/api/subfranchisor | In progress
Sub-Franchisee module | Internet Credits | Internet Credits workspace | /funding | API wiring | Do not swap loaders until VITE_API_BASE_URL is set | In progress
Sub-Franchisee module | Internet Credits | Internet Credits workspace | /funding | QA / verification | Pending verification | To do
Sub-Franchisee module | Internet Credits | Internet Credits workspace | /funding | Documentation | Covered in app-modules / user guide | Completed
Sub-Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | Initial UI/UX | Sub → Franchisee hop (default 70%) | Completed
Sub-Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | Frontend implementation | Overrides in esarisari_deposit_rates | Completed
Sub-Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | API-ready client | Unwired client in src/services/api/subfranchisor | In progress
Sub-Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | API wiring | Do not swap loaders until VITE_API_BASE_URL is set | In progress
Sub-Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | QA / verification | Pending verification | To do
Sub-Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | Documentation | Covered in app-modules / user guide | Completed
Sub-Franchisee module | Commission Settings | Commission Settings | /commission-settings | Initial UI/UX | Retailer, franchisee, Your Share editable; platform fee read-only | Completed
Sub-Franchisee module | Commission Settings | Commission Settings | /commission-settings | Frontend implementation | Split is % of sales; total must equal 100% | Completed
Sub-Franchisee module | Commission Settings | Commission Settings | /commission-settings | API-ready client | Unwired client in src/services/api/subfranchisor | In progress
Sub-Franchisee module | Commission Settings | Commission Settings | /commission-settings | API wiring | Do not swap loaders until VITE_API_BASE_URL is set | In progress
Sub-Franchisee module | Commission Settings | Commission Settings | /commission-settings | QA / verification | Pending verification | To do
Sub-Franchisee module | Commission Settings | Commission Settings | /commission-settings | Documentation | Covered in app-modules / user guide | Completed
Sub-Franchisee module | Transactions | Transactions Ledger | /transactions | Initial UI/UX | Network sales; Your Share column; no Record sale | Completed
Sub-Franchisee module | Transactions | Transactions Ledger | /transactions | Frontend implementation | Scoped by subfranchiseeOrganizationId | Completed
Sub-Franchisee module | Transactions | Transactions Ledger | /transactions | API-ready client | Unwired client in src/services/api/subfranchisor | In progress
Sub-Franchisee module | Transactions | Transactions Ledger | /transactions | API wiring | Do not swap loaders until VITE_API_BASE_URL is set | In progress
Sub-Franchisee module | Transactions | Transactions Ledger | /transactions | QA / verification | Pending verification | To do
Sub-Franchisee module | Transactions | Transactions Ledger | /transactions | Documentation | Covered in app-modules / user guide | Completed
Sub-Franchisee module | Revenue | Revenue | /revenue | Initial UI/UX | IC spread earnings + sales commission | Completed
Sub-Franchisee module | Revenue | Revenue | /revenue | Frontend implementation | credit_spread mode; no franchise collections | Completed
Sub-Franchisee module | Revenue | Revenue | /revenue | API-ready client | Unwired client in src/services/api/subfranchisor | In progress
Sub-Franchisee module | Revenue | Revenue | /revenue | API wiring | Do not swap loaders until VITE_API_BASE_URL is set | In progress
Sub-Franchisee module | Revenue | Revenue | /revenue | QA / verification | Pending verification | To do
Sub-Franchisee module | Revenue | Revenue | /revenue | Documentation | Covered in app-modules / user guide | Completed
Sub-Franchisee module | Reports | Reports | /reports | Initial UI/UX | Revenue Sharing Sub-Franchisee table + CSV + network commissions | Completed
Sub-Franchisee module | Reports | Reports | /reports | Frontend implementation | Client-sheet layout; platform fee excluded from Total Revenue | Completed
Sub-Franchisee module | Reports | Reports | /reports | API-ready client | Unwired client in src/services/api/subfranchisor | In progress
Sub-Franchisee module | Reports | Reports | /reports | API wiring | Do not swap loaders until VITE_API_BASE_URL is set | In progress
Sub-Franchisee module | Reports | Reports | /reports | QA / verification | Pending verification | To do
Sub-Franchisee module | Reports | Reports | /reports | Documentation | Covered in app-modules / user guide | Completed

## Franchisee
Role | Module | Page | Path | Task title | Subtitle | Status
Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | Initial UI/UX | Greyed nav item only | Completed
Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | Frontend implementation | Role-specific franchisee dashboard | To do
Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | API-ready client | Not started | In progress
Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | API wiring | Blocked on product + API | In progress
Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | QA / verification | Route is blocked | To do
Franchisee module | Dashboard (greyed) | Dashboard | /dashboard | Documentation | Noted as greyed in app-modules | Completed
Franchisee module | Retailers (greyed) | Retailers | /retailers | Initial UI/UX | Greyed nav; placeholder page; route blocked | To do
Franchisee module | Retailers (greyed) | Retailers | /retailers | Frontend implementation | No retailer directory product yet | To do
Franchisee module | Retailers (greyed) | Retailers | /retailers | API-ready client | No contract yet | In progress
Franchisee module | Retailers (greyed) | Retailers | /retailers | API wiring | Blocked on frontend + API | In progress
Franchisee module | Retailers (greyed) | Retailers | /retailers | QA / verification | Page is not live | To do
Franchisee module | Retailers (greyed) | Retailers | /retailers | Documentation | Placeholder only in app-modules | In progress
Franchisee module | Wallets | Wallet Management | /wallet-management | Initial UI/UX | Own + retailer credits directory | Completed
Franchisee module | Wallets | Wallet Management | /wallet-management | Frontend implementation | Read-only localStorage wallets | Completed
Franchisee module | Wallets | Wallet Management | /wallet-management | API-ready client | Need franchisee API module (same pattern as Sub) | In progress
Franchisee module | Wallets | Wallet Management | /wallet-management | API wiring | Still on localStorage | In progress
Franchisee module | Wallets | Wallet Management | /wallet-management | QA / verification | Pending verification | To do
Franchisee module | Wallets | Wallet Management | /wallet-management | Documentation | Covered in app-modules / user guide | Completed
Franchisee module | Internet Credits | Internet Credits workspace | /funding | Initial UI/UX | Request from Sub; release/reject retailer requests; direct release | Completed
Franchisee module | Internet Credits | Internet Credits workspace | /funding | Frontend implementation | Hop sub_to_franchisee / franchisee_to_retailer | Completed
Franchisee module | Internet Credits | Internet Credits workspace | /funding | API-ready client | Need franchisee API module (same pattern as Sub) | In progress
Franchisee module | Internet Credits | Internet Credits workspace | /funding | API wiring | Still on localStorage | In progress
Franchisee module | Internet Credits | Internet Credits workspace | /funding | QA / verification | Pending verification | To do
Franchisee module | Internet Credits | Internet Credits workspace | /funding | Documentation | Covered in app-modules / user guide | Completed
Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | Initial UI/UX | Franchisee → Retailer hop (default 80%) | Completed
Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | Frontend implementation | Downline overrides only | Completed
Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | API-ready client | Need franchisee API module (same pattern as Sub) | In progress
Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | API wiring | Still on localStorage | In progress
Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | QA / verification | Pending verification | To do
Franchisee module | Deposit Rates | Deposit Rates | /deposit-rates | Documentation | Covered in app-modules / user guide | Completed
Franchisee module | Transactions | Transactions Ledger | /transactions | Initial UI/UX | Retailer sales under this franchisee | Completed
Franchisee module | Transactions | Transactions Ledger | /transactions | Frontend implementation | Scoped by franchiseeOrganizationId | Completed
Franchisee module | Transactions | Transactions Ledger | /transactions | API-ready client | Need franchisee API module (same pattern as Sub) | In progress
Franchisee module | Transactions | Transactions Ledger | /transactions | API wiring | Still on localStorage | In progress
Franchisee module | Transactions | Transactions Ledger | /transactions | QA / verification | Pending verification | To do
Franchisee module | Transactions | Transactions Ledger | /transactions | Documentation | Covered in app-modules / user guide | Completed
Franchisee module | Revenue | Revenue | /revenue | Initial UI/UX | IC spread + sales commission | Completed
Franchisee module | Revenue | Revenue | /revenue | Frontend implementation | credit_spread mode | Completed
Franchisee module | Revenue | Revenue | /revenue | API-ready client | Need franchisee API module (same pattern as Sub) | In progress
Franchisee module | Revenue | Revenue | /revenue | API wiring | Still on localStorage | In progress
Franchisee module | Revenue | Revenue | /revenue | QA / verification | Pending verification | To do
Franchisee module | Revenue | Revenue | /revenue | Documentation | Covered in app-modules / user guide | Completed
Franchisee module | Reports | Reports | /reports | Initial UI/UX | Retailer commissions + IC earnings; no Sub sheet table | Completed
Franchisee module | Reports | Reports | /reports | Frontend implementation | Role config hides Sub revenue-sharing export | Completed
Franchisee module | Reports | Reports | /reports | API-ready client | Need franchisee API module (same pattern as Sub) | In progress
Franchisee module | Reports | Reports | /reports | API wiring | Still on localStorage | In progress
Franchisee module | Reports | Reports | /reports | QA / verification | Pending verification | To do
Franchisee module | Reports | Reports | /reports | Documentation | Covered in app-modules / user guide | Completed

## Retailer
Role | Module | Page | Path | Task title | Subtitle | Status
Retailer module | Dashboard (greyed) | Dashboard | /dashboard | Initial UI/UX | Greyed nav item only | Completed
Retailer module | Dashboard (greyed) | Dashboard | /dashboard | Frontend implementation | Role-specific retailer dashboard | To do
Retailer module | Dashboard (greyed) | Dashboard | /dashboard | API-ready client | Not started | In progress
Retailer module | Dashboard (greyed) | Dashboard | /dashboard | API wiring | Blocked on product + API | In progress
Retailer module | Dashboard (greyed) | Dashboard | /dashboard | QA / verification | Route is blocked | To do
Retailer module | Dashboard (greyed) | Dashboard | /dashboard | Documentation | Noted as greyed in app-modules | Completed
Retailer module | Wallet | Wallet | /wallet | Initial UI/UX | Available Credits, sale margin, request CTA | Completed
Retailer module | Wallet | Wallet | /wallet | Frontend implementation | Retailer operating wallet; cannot record sales here | Completed
Retailer module | Wallet | Wallet | /wallet | API-ready client | Need retailer API module | In progress
Retailer module | Wallet | Wallet | /wallet | API wiring | Still on localStorage | In progress
Retailer module | Wallet | Wallet | /wallet | QA / verification | Pending verification | To do
Retailer module | Wallet | Wallet | /wallet | Documentation | Covered in app-modules / user guide | Completed
Retailer module | Internet Credits | Request Funding | /request-funding | Initial UI/UX | Request-only workspace to Franchisee | Completed
Retailer module | Internet Credits | Request Funding | /request-funding | Frontend implementation | Same FundingWorkspacePage; no incoming / direct release | Completed
Retailer module | Internet Credits | Request Funding | /request-funding | API-ready client | Need retailer API module | In progress
Retailer module | Internet Credits | Request Funding | /request-funding | API wiring | Still on localStorage | In progress
Retailer module | Internet Credits | Request Funding | /request-funding | QA / verification | Pending verification | To do
Retailer module | Internet Credits | Request Funding | /request-funding | Documentation | Covered in app-modules / user guide | Completed
Retailer module | Transactions | Transactions Ledger | /transactions | Initial UI/UX | Own sales + Record demo sale | Completed
Retailer module | Transactions | Transactions Ledger | /transactions | Frontend implementation | Burns ~97% credits; stamps commission % of sales | Completed
Retailer module | Transactions | Transactions Ledger | /transactions | API-ready client | Need retailer API module | In progress
Retailer module | Transactions | Transactions Ledger | /transactions | API wiring | Still on localStorage | In progress
Retailer module | Transactions | Transactions Ledger | /transactions | QA / verification | Pending verification | To do
Retailer module | Transactions | Transactions Ledger | /transactions | Documentation | Covered in app-modules / user guide | Completed
Retailer module | Revenue | Revenue | /revenue | Initial UI/UX | Your commission, sales volume, credits consumed | Completed
Retailer module | Revenue | Revenue | /revenue | Frontend implementation | No IC earnings / Total earnings cards | Completed
Retailer module | Revenue | Revenue | /revenue | API-ready client | Need retailer API module | In progress
Retailer module | Revenue | Revenue | /revenue | API wiring | Still on localStorage | In progress
Retailer module | Revenue | Revenue | /revenue | QA / verification | Pending verification | To do
Retailer module | Revenue | Revenue | /revenue | Documentation | Covered in app-modules / user guide | Completed
Retailer module | Reports | Reports | /reports | Initial UI/UX | Own sales commission + volume; limited CSV | Completed
Retailer module | Reports | Reports | /reports | Frontend implementation | No network tables or Sub sheet | Completed
Retailer module | Reports | Reports | /reports | API-ready client | Need retailer API module | In progress
Retailer module | Reports | Reports | /reports | API wiring | Still on localStorage | In progress
Retailer module | Reports | Reports | /reports | QA / verification | Pending verification | To do
Retailer module | Reports | Reports | /reports | Documentation | Covered in app-modules / user guide | Completed