eSariSari Float Management — Implementation status

1 September 2026  ·  Client summary

Live demo screens are in place for the modules below. Remaining work follows the delivery timeline.

# Delivery timeline

| Week | Focus |
| --- | --- |
| 1–6 September | Complete remaining implementation (API client and API wiring). |
| 7–12 September | Staging environment preparation, and QA and UAT. |
| 14–18 September | Production readiness, go-live, and handover. |

40 pages  ·  111 completed  ·  82 in progress  ·  47 to do.

Completed = live in the current demo.  In progress = remaining implementation (API client and API wiring).  To do = QA/UAT, or not live for that role.  Pages marked (not live) are greyed in the app and not part of this release.

# Shared (all roles)

Sign-in, profile, and notifications used by every role.

| Module | Page | UI / UX | Frontend | API client | API wiring | QA/UAT | Docs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Authentication & chrome | Login | Completed | Completed | In progress | In progress | To do | Completed |
|  | Profile | Completed | Completed | In progress | In progress | To do | Completed |
|  | Notifications | Completed | Completed | In progress | In progress | To do | Completed |

# Admin

Franchise setup, collections, network credits, and sales ledger.

| Module | Page | UI / UX | Frontend | API client | API wiring | QA/UAT | Docs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financials Dashboard | Dashboard | Completed | Completed | In progress | In progress | To do | Completed |
| Clients & franchise setup | Clients list | Completed | Completed | In progress | In progress | To do | Completed |
|  | Client details | Completed | Completed | In progress | In progress | To do | Completed |
|  | Onboarding step 1 — Client Info | Completed | Completed | In progress | In progress | To do | Completed |
|  | Onboarding step 2 — Franchise Setup | Completed | Completed | In progress | In progress | To do | Completed |
|  | Onboarding step 3 — Revenue Split | Completed | Completed | In progress | In progress | To do | Completed |
|  | Onboarding step 4 — Review | Completed | Completed | In progress | In progress | To do | Completed |
| Wallets | Wallets directory | Completed | Completed | In progress | In progress | To do | Completed |
| Internet Credits | Internet Credits workspace | Completed | Completed | In progress | In progress | To do | Completed |
| Deposit Rates | Deposit Rates | Completed | Completed | In progress | In progress | To do | Completed |
| Commission Settings | Commission Settings | Completed | Completed | In progress | In progress | To do | Completed |
| Transactions | Transactions Ledger | Completed | Completed | In progress | In progress | To do | Completed |
| Revenue | Revenue | Completed | Completed | In progress | In progress | To do | Completed |
| Reports | Reports | Completed | Completed | In progress | In progress | To do | Completed |

# Sub-Franchisee

Wallets, credits, rates, commission, sales, and reports.

| Module | Page | UI / UX | Frontend | API client | API wiring | QA/UAT | Docs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Dashboard (not live) | Dashboard | Completed | To do | In progress | In progress | To do | Completed |
| Franchisees (not live) | Franchisees | To do | To do | In progress | In progress | To do | In progress |
| Wallets | Wallet Management | Completed | Completed | In progress | In progress | To do | Completed |
| Internet Credits | Internet Credits workspace | Completed | Completed | In progress | In progress | To do | Completed |
| Deposit Rates | Deposit Rates | Completed | Completed | In progress | In progress | To do | Completed |
| Commission Settings | Commission Settings | Completed | Completed | In progress | In progress | To do | Completed |
| Transactions | Transactions Ledger | Completed | Completed | In progress | In progress | To do | Completed |
| Revenue | Revenue | Completed | Completed | In progress | In progress | To do | Completed |
| Reports | Reports | Completed | Completed | In progress | In progress | To do | Completed |

# Franchisee

Same operational pages as Sub, scoped to this franchisee’s retailers.

| Module | Page | UI / UX | Frontend | API client | API wiring | QA/UAT | Docs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Dashboard (not live) | Dashboard | Completed | To do | In progress | In progress | To do | Completed |
| Retailers (not live) | Retailers | To do | To do | In progress | In progress | To do | In progress |
| Wallets | Wallet Management | Completed | Completed | In progress | In progress | To do | Completed |
| Internet Credits | Internet Credits workspace | Completed | Completed | In progress | In progress | To do | Completed |
| Deposit Rates | Deposit Rates | Completed | Completed | In progress | In progress | To do | Completed |
| Transactions | Transactions Ledger | Completed | Completed | In progress | In progress | To do | Completed |
| Revenue | Revenue | Completed | Completed | In progress | In progress | To do | Completed |
| Reports | Reports | Completed | Completed | In progress | In progress | To do | Completed |

# Retailer

Wallet, request credits, record sales, and own commission.

| Module | Page | UI / UX | Frontend | API client | API wiring | QA/UAT | Docs |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Dashboard (not live) | Dashboard | Completed | To do | In progress | In progress | To do | Completed |
| Wallet | Wallet | Completed | Completed | In progress | In progress | To do | Completed |
| Internet Credits | Request Funding | Completed | Completed | In progress | In progress | To do | Completed |
| Transactions | Transactions Ledger | Completed | Completed | In progress | In progress | To do | Completed |
| Revenue | Revenue | Completed | Completed | In progress | In progress | To do | Completed |
| Reports | Reports | Completed | Completed | In progress | In progress | To do | Completed |

Dashboard / Franchisees / Retailers marked (not live) stay out of this release unless requested.